## 2025 V2 (Worst Case) (hidden)
Task | Mandays | October |  |  |  |  | November |  |  |  | Desember |  |  |  |  | Color Terms
|  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 |  | PM
URS Creation | 10 | [15 empty] | UI/UX Team | bar: October W1 to November W3
URS Approval | 5 | [15 empty] | SWE Team | bar: November W3 to Desember W1
Create UI | 25 | [15 empty] | AI Team | bar: October W1 to October W5
Login Page | 5 | [15 empty] | Done | bar: October W1
Chatbot UI | 5 | [15 empty] | Users | bar: October W1
Discovery & Architecture | 15 | bar: October W1 to October W3
Environment & Vector Store Setup | 13 | bar: October W2 to October W4
Ingestion Pipeline - Include Layout Detection - Include OCR - Include img2table - Multi-column handling | 35 | bar: October W3 to November W4
Retrieval and Prompting | 30 | bar: October W4 to November W4
Experimenting with Different LLM | 10 | bar: October W4 to October W5
Validation & Guardrails | 25 | bar: November W2 to Desember W2
Lobechat Integration | 8 | bar: November W3 to November W4
Reranking & Tuning | 6 | bar: November W4 to Desember W1
Security, Roles, & Observability | 6 | bar: Desember W2 to Desember W3
AI Deployment | 20 | bar: Desember W3 to Desember W5
Connect FE to Biomni | 25 | bar: October W2 to November W1
Paper Management UI | 5 | bar: October W2
Paper Management BE | 15 | bar: October W3 to October W5
User Management -RBAC | 5 | bar: October W5
Audit Trail -UI | 5 | bar: November W1
Audit Trail BE | 15 | bar: November W2 to November W4
Bug Fixing and Improvement | 15 | bar: Desember W1 to Desember W5
SWE Deployment to Staging Cloud | 20 | bar: Desember W2 to Desember W3
Create Validating ingestion pipeline Web for BioLLM | bar: Desember W3 to Desember W4
Validating BioPaperExtractor & BioLLM | bar: Desember W4 to Desember W5
Improve BioPaperExtractor & BioLLM | bar: Desember W4 to Desember W5
UAT | bar: Desember W5
Deployment to Production | bar: Desember W5

## 2025 V1 (hidden)
Task | Mandays | October |  |  |  |  | November |  |  |  | Desember |  |  |  |  | Color Terms
|  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 |  | PM
URS Creation | 10 | [15 empty] | UI/UX Team | bar: October W1 to November W3
URS Approval | 5 | [15 empty] | SWE Team | bar: November W3 to Desember W1
Create UI | 25 | [15 empty] | AI Team | bar: October W1 to October W5
Login Page | 5 | [15 empty] | Done | bar: October W1
Chatbot UI | 5 | bar: October W1
Discovery & Architecture | 15 | bar: October W1 to October W3
Environment & Vector Store Setup | 13 | bar: October W2 to October W4
Ingestion Pipeline - Include Layout Detection - Include OCR - Include img2table - Multi-column handling | 35 | bar: October W3 to November W4
Retrieval and Prompting | 30 | bar: October W4 to November W4
Experimenting with Different LLM | 10 | bar: October W4 to October W5
Validation & Guardrails | 25 | bar: November W2 to Desember W2
Lobechat Integration | 8 | bar: November W3 to November W4
Reranking & Tuning | 6 | bar: November W4 to Desember W1
Security, Roles, & Observability | 6 | bar: Desember W2 to Desember W3
AI Deployment | 20 | bar: Desember W3 to Desember W5
Connect FE to Biomni | 25 | bar: October W2 to November W1
Paper Management UI | 5 | bar: October W2
Paper Management BE | 15 | bar: October W3 to October W5
User Management -RBAC | 5 | bar: October W5
Audit Trail -UI | 5 | bar: November W1
Audit Trail BE | 15 | bar: November W2 to November W4
Bug Fixing and Improvement | 15 | bar: Desember W1 to Desember W3
SWE Deployment to Staging Cloud | 20 | bar: Desember W2 to Desember W5

## 2025 V2 (Best Case)
Task | Phase | Mandays | October |  |  |  |  | November |  |  |  | Desember |  |  |  |  | January 2026 |  |  |  | Color Terms
|  |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 |  | PM
URS Creation | Planning | 10 | [19 empty] | UI/UX Team | bar: October W1 to November W3
URS Approval | Planning | 5 | [19 empty] | SWE Team | bar: November W3 to Desember W1
Create UI | Design | 25 | [19 empty] | AI Team | bar: October W1 to October W5
Login Page | Development | 5 | [19 empty] | Done | bar: October W1
Chatbot UI | Development | 5 | [19 empty] | Users | bar: October W1
Discovery & Architecture | Development | 15 | bar: October W1 to October W3
Environment & Vector Store Setup | Development | 13 | bar: October W2 to October W4
Ingestion Pipeline - Include Layout Detection - Include OCR - Include img2table - Multi-column handling | Development | 35 | bar: October W3 to November W4
Retrieval and Prompting | Development | 30 | bar: October W4 to November W4
Experimenting with Different LLM | Development | 10 | bar: October W4 to October W5
Validation & Guardrails | Development | 25 | bar: November W2 to Desember W2
Lobechat Integration | Development | 8 | bar: November W3 to November W4
Reranking & Tuning | Development | 6 | bar: November W4 to Desember W1
Security, Roles, & Observability | Development | 6 | bar: Desember W2 to Desember W3
AI Deployment | Development | 20 | bar: Desember W3 to Desember W5
Connect FE to Biomni | Development | 25 | bar: October W2 to November W1
Paper Management UI | Development | 5 | bar: October W2
Paper Management BE | Development | 15 | bar: October W3 to October W5
User Management -RBAC | Development | 5 | bar: October W5
Audit Trail -UI | Development | 5 | bar: November W1
Audit Trail BE | Development | 15 | bar: November W2 to November W4
Bug Fixing and Improvement | Development | 15 | bar: Desember W1 to Desember W3
SWE Deployment to Staging Cloud | Development | 20 | bar: Desember W2 to Desember W3
UAT & Human Feedback | Testing & Validation | 10 | bar: January 2026 W3 to January 2026 W4
Deployment to Production Environment (TBD) Waiting for AWS Bedrock Services Innolab & Data Center Infra | Deployment | bar: January 2026 W4

## 2026 V1
Task | Phase | Mandays | January 2026 |  |  |  | Februrary 2026 |  |  |  | March 2026 |  |  |  | April 2026 |  |  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3
User Management -RBAC | Development | 10 | bar: Februrary 2026 W1 to Februrary 2026 W2
Design/propose validation method for end-to-end LLM chatbot | Development | 5 | bar: January 2026 W3
Design/propose validation method for retrieval system | Development | 5 | bar: January 2026 W3
Design/propose validation method for end-to-end LLM chatbot | Development | 15 | bar: January 2026 W3 to Februrary 2026 W1
Run system evaluation again for 2nd Data Ingestion pipeline | Development | 10 | bar: Februrary 2026 W1 to Februrary 2026 W2
Create Evaluation Pipeline using the agreed 2-stage evaluation metrics | Development | 15 | bar: January 2026 W3 to Februrary 2026 W2
Run evaluation on current Paper Extractor implemented algorithm | Development | 10 | bar: Februrary 2026 W2 to Februrary 2026 W3
UAT & Human Feedback | Testing & Validation | 5 | bar: Februrary 2026 W4 to March 2026 W1
Migrate from cloud infra to on prem (Staging) | Deployment | 10 | bar: Februrary 2026 W2 to Februrary 2026 W3
Improvement the AI Assistant | Development | 110 | bar: Februrary 2026 W2 to June 2026 W3
Create 2nd Data Ingestion pipeline (+ caching) to accommodate AWS stack | Development | 40 | bar: April 2026 W1 to April 2026 W4
Ingest Paper using AWS Embedding | Development | 40 | bar: April 2026 W1 to April 2026 W4
Run system evaluation again for 2nd Data Ingestion pipeline | Development | 40 | bar: April 2026 W1 to April 2026 W4
UAT & Human Feedback | Testing & Validation | 5 | bar: May 2026 W1
Deployment on prem and Server rReady | Deployment | 15 | bar: May 2026 W1 to May 2026 W3
Color Terms
PM
UI/UX Team
SWE Team
AI Team
Done
Users

## 2025 V2 (Best Case) (2)
No | Task | Phase | Mandays | October |  |  |  |  | November |  |  |  | Desember |  |  |  |  | January 2026 |  |  |  | Februrary 2026 |  |  |  | March 2026 |  |  |  | April 2026 |  |  |  | May 2026 |  |  |  | June 2026 |  |  |  | July 2026 |  |  | Color Terms
|  |  |  | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 |  | PM
1 | [PM] - URS Creation | Planning | 10 | [42 empty] | UI/UX Team | bar: October W1 to November W3
2 | [PM] - URS Approval | Planning | 5 | [42 empty] | SWE Team | bar: November W3 to Desember W1
3 | [UI] - Create UI | Design | 25 | [42 empty] | AI Team | bar: October W1 to October W5
4 | [UI] - Login Page | Development | 5 | [42 empty] | Done | bar: October W1
5 | [UI] - Chatbot UI | Development | 5 | [42 empty] | Users | bar: October W1
6 | [AI] - Discovery & Architecture | Development | 15 | bar: October W1 to October W3
7 | [AI] - Environment & Vector Store Setup | Development | 13 | bar: October W2 to October W4
8 | [AI] - Ingestion Pipeline - Include Layout Detection - Include OCR - Include img2table - Multi-column handling | Development | 35 | bar: October W3 to November W4
9 | [AI] - Retrieval and Prompting | Development | 30 | bar: October W4 to November W4
10 | [AI] - Experimenting with Different LLM | Development | 10 | bar: October W4 to October W5
11 | [AI] - Validation & Guardrails | Development | 25 | bar: November W2 to Desember W2
12 | [AI] - Lobechat Integration | Development | 8 | bar: November W3 to November W4
13 | [AI] - Reranking & Tuning | Development | 6 | bar: November W4 to Desember W1
14 | [AI] - Security, Roles, & Observability | Development | 6 | bar: Desember W2 to Desember W3
15 | [AI] - AI Deployment | Development | 20 | bar: Desember W3 to Desember W5
16 | [SWE] - Connect FE to Biomni | Development | 25 | bar: October W2 to November W1
17 | [SWE] - Paper Management UI | Development | 5 | bar: October W2
18 | [SWE] - Paper Management BE | Development | 15 | bar: October W3 to October W5
19 | [SWE] - User Management -RBAC | Development | 5 | bar: October W5
20 | [SWE] - Audit Trail -UI | Development | 5 | bar: November W1
21 | [SWE] - Audit Trail BE | Development | 15 | bar: November W2 to November W4
22 | [SWE] - Bug Fixing and Improvement | Development | 15 | bar: Desember W1 to Desember W3
23 | [SWE] - Deployment to Staging Cloud | Development | 20 | bar: Desember W2 to Desember W3
24 | [BioLLM & BioPaperExtractor] Design/propose validation method for retrieval system | Development | 5 | bar: January 2026 W3
25 | [BioLLM] Design/propose validation method for end-to-end LLM chatbot | Development | 15 | bar: January 2026 W3 to Februrary 2026 W1
26 | [BioPaperExtractor] Create Evaluation Pipeline using the agreed 2-stage evaluation metrics | Development | 20 | bar: January 2026 W3 to Februrary 2026 W2
27 | [KalbeGPT] User Management -RBAC | Development | 10 | bar: Februrary 2026 W1 to Februrary 2026 W2
28 | [BioLLM] Validator Feedback Execution | Testing & Validation | bar: January 2026 W1 to January 2026 W2
29 | [BioLLM] Evaluate feasibility and performance of AWS embedding vs Open AI embedding model | Testing & Validation | 10 | bar: January 2026 W3 to January 2026 W4
30 | [BioLLM] Improve agent capability based on Validator feedback | Testing & Validation | bar: January 2026 W4 to March 2026 W1
31 | [BioPaperExtractor] Run evaluation on current Paper Extractor implemented algorithm | Testing & Validation | 30 | bar: Februrary 2026 W2 to March 2026 W3
32 | [BioLLM] Migrate from cloud infra to on prem (Staging) | Deployment | 10 | bar: Februrary 2026 W2 to March 2026 W2
33 | [BioLLM] UAT | Testing & Validation | 1 | bar: March 2026 W3
34 | [BioLLM] Deliver BioLLM | Deliver | 1 | bar: March 2026 W3
35 | [BioLLM & BioPaperExtractor] Improvement the AI Assistant | Development | 110 | bar: April 2026 W1 to July 2026 W3
36 | [BioLLM] Create 2nd Data Ingestion pipeline (+ caching) to accommodate AWS stack | Development | 40 | bar: April 2026 W1 to May 2026 W4
37 | [BioLLM] Ingest Paper using AWS Embedding | Development | 40 | bar: April 2026 W1 to May 2026 W4
38 | [BioPaperExtractor] UAT & Human Feedback BioPaperExtractor | Testing & Validation | 1
39 | [BioPaperExtractor] Deliver BioPaperExtractor | Deliver | 1
40 | [BioLLM & BioPaperExtractor] UAT & Human Feedback (after migrate to AWS) | Testing & Validation | 5
41 | [KalbeGPT] Deployment on prem and Server Ready | Deployment | 15