## ELN Timeline
Task Subject | Plan Start | Plan End | Actual Start | Actual End
Feedback Gathering Module 1-5 | 2026-01-01 | 2026-03-31 | 2026-01-04 | 2026-03-29
Development Module 4-5 | 2026-01-01 | 2026-03-31 | 2026-01-03 | 2026-03-31
Implementasi Feedback Development (Phase 1) | 2026-02-01 | 2026-05-31 | 2026-02-05 | 2026-06-02
Database Reagent, Sample, Working Standard | 2026-05-01 | 2026-06-30 | 2026-04-29 | 2026-06-29
Multiple Operator edit Procedure | 2026-05-01 | 2026-07-31 | 2026-05-04 | 2026-08-03
ERP Integration | 2026-03-01 | 2026-07-31 | 2026-03-03 | 2026-07-26
Infrastructure for Rail out | 2026-04-01 | 2026-07-31 | 2026-03-29 | 2026-08-04
UAT Protocol Drafting | 2026-01-01 | 2026-07-31 | 2026-01-06 | 2026-07-23
UAT Protocol Approval | 2026-01-01 | 2026-09-30
UAT Testing | 2026-06-01 | 2026-08-31
UAT Report | 2026-08-01 | 2026-09-30
Bug Fixing | 2026-08-01 | 2026-10-31
Roll out | 2026-09-01 | 2026-10-31
User Requirement Gathering Phase 2 | 2026-07-01 | 2026-09-30
URS Drafting Phase 2 | 2026-08-01 | 2026-11-30
URS Approval Phase 2 | 2026-09-01 | 2026-11-30
Phase 2 Development (advanced data analysis) | 2026-10-01 | 2026-12-31
User Manual Drafting | 2026-02-01 | 2026-06-30
User Manual Approval | 2026-04-01 | 2026-07-31
User Requirements Specification Drafting | 2026-02-01 | 2026-07-31
User Requirements Specification Approval | 2026-04-01 | 2026-08-31
Functional Specification Document Drafting | 2026-02-01 | 2026-08-31
Functional Specification Document Approval | 2026-04-01 | 2026-08-31
Software Detailed Design Specification Drafting | 2026-02-01 | 2026-08-31
Software Detailed Design Specification Approval | 2026-04-01 | 2026-08-31
Installation Qualification Drafting | 2026-02-01 | 2026-09-30
Installation Qualification Approval | 2026-05-01 | 2026-09-30
System Release Note Drafting | 2026-05-01 | 2026-10-31
System Release Note Approval | 2026-09-01 | 2026-10-31