## Timeline Elvasoft PACS Phase 2
BACKLOG | MONTH | PIC | STATUS (Dev + Testing) | JAN'26 |  |  |  | FEB'26 |  |  |  | MAR'26 |  |  |  | APR'26 |  |  |  |  | MAY'26 |  |  |  | JUN'26
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Able to revert synchronize | JAN | Jer | DONE | [25 empty] | Keterangan | bar: JAN'26 W1 to JAN'26 W4
Critical Value in Report | JAN | Ian | DONE | [26 empty] | Development | bar: JAN'26 W1 to JAN'26 W4
Double klik or one button trigger view report and open dicom viewer | JAN | Fito | DONE | [26 empty] | Testing by QA CIT | bar: JAN'26 W1 to JAN'26 W4
Adjust Column order and visibility | JAN | Ian | DONE | [26 empty] | Libur | bar: JAN'26 W1 to JAN'26 W4
Able to synchronise CR and DX modality (make sure show up in modality worklist) | JAN | Jer | DONE | [26 empty] | Testing by EMP, CDT, CIT | bar: JAN'26 W1 to JAN'26 W4
For CR study, able to assign DX ward. works for DX study too, able to assign CR ward | JAN | Jer | DONE | bar: JAN'26 W1 to JAN'26 W4
Redesign DICOM Asset in DCM4CHEE | JAN | Ian | DONE | bar: JAN'26 W1 to JAN'26 W4
Report finder | JAN | Ian | DONE | bar: JAN'26 W1 to JAN'26 W4
Single tap study to select Study | JAN | Ian | DONE | bar: JAN'26 W1 to JAN'26 W4
Double tap study to open with OHIF | JAN | Ian | DONE | bar: JAN'26 W1 to JAN'26 W4
[DICOM Viewer] Tools "CTR" untuk garis vertikal bisa diadjust, ga harus tegak lurus ngikutin garis yang panjang | JAN | Fei | DONE | bar: JAN'26 W1 to JAN'26 W4
[Toolkit - Ward Management] Memasukkan value "ruangan tempat melakukan pencitraan" ke server | JAN | Ian | DONE | bar: JAN'26 W1 to JAN'26 W4
Able to read Unscheduled Study to All Doctor | FEB | Jer | DONE | bar: FEB'26 W1 to FEB'26 W4
Logic for read unscheduled study (dashboard, performance, sync, etc) | FEB | Jer | DONE | bar: FEB'26 W1 to FEB'26 W4
RIS and PACS Fully Functional Mobility (Report) | FEB | Ian | DONE | bar: FEB'26 W1 to FEB'26 W4
Change Process Status Icon: Tutorial | FEB | Ian | DONE | bar: FEB'26 W1 to FEB'26 W4
Extract Dose Value from DICOM (if data exist) to RIS + DICOM Tag Management | FEB | Fito | DONE | bar: FEB'26 W1 to FEB'26 W4
[QR] QR code buat liat report (export) | FEB | Jer | DONE | bar: FEB'26 W1 to FEB'26 W4
Download Dose as Excel | FEB | Fito | DONE | bar: FEB'26 W1 to FEB'26 W4
Resolve distorted OHIF images / Migrate to OHIF version 3.11.0 | FEB | Fei | DONE | bar: FEB'26 W1 to FEB'26 W4
Extend DICOM menu : DICOM Send (send DICOM to other DICOM server) + CD Publisher | FEB | Hosi, Fito | DONE | bar: FEB'26 W1 to FEB'26 W4
Change Process Filter Function Mechanism | MAR | Ian | DONE | bar: MAR'26 W1 to MAR'26 W2; MAR'26 W4
Tombol Hide untuk menampilkan dan menyembunyikan tools DICOM Viewer & Hide mode "Segmentation" on DICOM Viewer | MAR | Fei | DONE | bar: MAR'26 W1 to MAR'26 W2; MAR'26 W4
Upon Read verified, CITO value will be inactive/false | MAR | Jer | DONE | bar: MAR'26 W1 to MAR'26 W2; MAR'26 W4
Untuk tampilan informasi pasien di DICOM Viewer harus diletakin di 1 tempat untuk kebutuhan melihat secara jelas | MAR | Fei | DONE | bar: MAR'26 W1 to MAR'26 W2; MAR'26 W4
[Report] Remove 2 other fields, only keep findings field | MAR | Fito | DONE | bar: MAR'26 W1 to MAR'26 W2; MAR'26 W4
OHIF adjust font size | MAR | Fito | DONE | bar: MAR'26 W1 to MAR'26 W2; MAR'26 W4
Extend DICOM menu : Download DICOM with DICOM Viewer | MAR | Jer | DONE | bar: MAR'26 W1 to MAR'26 W2; MAR'26 W4
Readjust Setup Share Template | MAR | Jer | DONE | bar: MAR'26 W1 to MAR'26 W2; MAR'26 W4
Able to change CITO value after DICOM received | APR | Jer | DONE DEV | bar: APR'26 W1 to APR'26 W5
Ubah metadata DICOM di RIS (Patient Name, MRN, Modality) | APR | Jer | DONE DEV | bar: APR'26 W1 to APR'26 W5
[Report] Auto-complete findings using specific terms | APR | Ian | DONE DEV | bar: APR'26 W1 to APR'26 W5
License | APR | Hosi | ON DEV | bar: APR'26 W1 to APR'26 W5
Extend DICOM menu : CD Burner | APR | Hosi, Fito | ON DEV | bar: APR'26 W1 to APR'26 W5
Stock Opname and Stock Management | APR | Jer | DONE DEV | bar: APR'26 W1 to MAY'26 W4
Redesign OHIF (Layout + Warna) | MAY | Fei | NOT STARTED | bar: MAY'26 W1 to MAY'26 W4
Simplify Header and Study List | MAY | Ian | NOT STARTED | bar: MAY'26 W1 to MAY'26 W4
History Study | MAY | Ian | NOT STARTED | bar: MAY'26 W1 to MAY'26 W4
Able to change Radiografer in RIS after DICOM received | MAY | Jer | NOT STARTED | bar: MAY'26 W1 to MAY'26 W4
Refresh Feature | MAY | Jer | NOT STARTED | bar: MAY'26 W1 to MAY'26 W4
Simplify button above study list using more button (+ drawer) | MAY | Jer | NOT STARTED | bar: MAY'26 W1 to MAY'26 W4
Extend DICOM menu : DICOM Print (Film Print) | MAY | Hosi | NOT STARTED | bar: MAY'26 W1 to MAY'26 W4
End-to-end Testing (with EMP) | JUN | CDT, EMP | NOT STARTED | bar: JUN'26 W1 to JUN'26 W4