## (Updated) Timeline Kalbe RIM
Project Manager Name =
No | Activity | Activity Desc | Type | Task | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | 2026-01-26 |  |  |  | 2026-02-26 |  |  |  | 2026-03-26 |  |  |  | 2026-04-26 |  |  |  |  | 2026-05-26 |  |  |  | 2026-06-26 |  |  |  | 2026-07-26 |  |  |  | 2026-08-26 |  |  |  | 2026-09-26 |  |  |  | 2026-10-26
[9 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
| Functional Spec Document | Functional Spec Document | bar: 2026-01-26 W1 to 2026-01-26 W4
| Development Phase | Development Phase | bar: 2026-01-26 W1 to 2026-02-26 W4
| Design Spec Document | Design Spec Document | bar: 2026-02-26 W1 to 2026-04-26 W1
| Data Import to Kalbe RIM | Data Import to Kalbe RIM | bar: 2026-02-26 W2 to 2026-03-26 W2
| Bug Fixing | RA-Document Detail Promote Demote ActionList
| 1 | Filter Dashboard based on Company Access | Bug Fixing | SWE | bar: 2026-03-26 W1
| 2 | Authorization Check for Reject Dossier/Document InfoCenter | Bug Fixing | SWE | bar: 2026-03-26 W1
| 3 | Dashboard Filter Data Based on Primary Company Access | Bug Fixing | SWE | bar: 2026-03-26 W1
| 4 | Checkout/Cancel Flow | Bug Fixing | SWE | bar: 2026-03-26 W1
| 5 | Flow Drag n Drop File from Local to VDM | Bug Fixing | SWE | bar: 2026-03-26 W2
| 6 | Promote Dossier (PhBR) - Popup Improvement | Bug Fixing | SWE | bar: 2026-03-26 W2
| 7 | Create submission dossier message error UI bug | Bug Fixing | SWE | bar: 2026-03-26 W2
| 8 | Optimize data table | Bug Fixing | SWE | bar: 2026-03-26 W2
| 9 | Update Structure VDM for Dossier & SubDossier | Bug Fixing | SWE | bar: 2026-03-26 W2
| 10 | Validation Promote for Dossier & SubDossier VDM | Bug Fixing | SWE | bar: 2026-03-26 W2
| 11 | InfoCenter Debugging | Bug Fixing | SWE | bar: 2026-03-26 W3
| 12 | Info Center Features | Bug Fixing | SWE | bar: 2026-03-26 W3
| 13 | Dossier Features | Bug Fixing | SWE | bar: 2026-03-26 W3
| 14 | Sub-Dossier Features | Bug Fixing | SWE | bar: 2026-03-26 W3
| 15 | VDM Features | Bug Fixing | SWE | bar: 2026-03-26 W3
| 16 | Explorer Features | Bug Fixing | SWE | bar: 2026-03-26 W4
| 17 | Update Checklist for InfoCenter | Bug Fixing | SWE | bar: 2026-03-26 W4
| 18 | Optimize info center page | Bug Fixing | SWE | bar: 2026-03-26 W4
| 20 | Internal Test | Bug Fixing | PM | bar: 2026-03-26 W3 to 2026-03-26 W4
| 21 | Finalize Draft OQ Protocol | Documentation | PM | bar: 2026-03-26 W1 to 2026-03-26 W2
| 22 | Draft User Manual Kalbe RIM | User Manual | PM | bar: 2026-03-26 W2 to 2026-03-26 W4
| System Testing Overview | System Testing Overview | bar: 2026-02-26 W1 to 2026-03-26 W4
| IQ Protocol - Staging | IQ Protocol - Staging | bar: 2026-02-26 W4 to 2026-04-26 W2
| IQ Record Report - Staging | IQ Record Report - Staging | bar: 2026-03-26 W1 to 2026-03-26 W3
| OQ Protocol - Staging | OQ Protocol - Staging | bar: 2026-03-26 W2 to 2026-04-26 W1
| OQ Record - Staging | OQ Record - Staging | bar: 2026-04-26 W1 to 2026-04-26 W3
| Fixing Phase After OQ | Fixing Phase After OQ | bar: 2026-04-26 W2 to 2026-04-26 W3
| Re-OQ Record - Staging | Re-OQ Record - Staging | bar: 2026-04-26 W3 to 2026-04-26 W4
| OQ Report - Staging | OQ Report - Staging | bar: 2026-04-26 W3 to 2026-04-26 W4
| Deploy to Production Env | Deploy to Production Env | bar: 2026-04-26 W3 to 2026-04-26 W4
| IQ Protocol - Production | IQ Protocol - Production | bar: 2026-03-26 W3 to 2026-03-26 W4
| IQ Record Report - Production | IQ Record Report - Production | bar: 2026-04-26 W5 to 2026-05-26 W2
| PQ Protocol - Production | PQ Protocol - Production | bar: 2026-05-26 W3 to 2026-06-26 W2
| PQ Record - Production | PQ Record - Production | bar: 2026-05-26 W4 to 2026-06-26 W3
| Fixing Phase After PQ | Fixing Phase After PQ | bar: 2026-06-26 W2 to 2026-06-26 W3
| Re-PQ Record - Production | Re-PQ Record - Production
| Go-Live Preparation (RTM, RN, etc) | Go-Live Preparation (RTM, RN, etc) | bar: 2026-06-26 W4 to 2026-07-26 W3
| Training User | Training User | bar: 2026-06-26 W4 to 2026-07-26 W3