## Gantt
Project Portfolio Gantt Chart
Monthly view • 2025-01 to 2026-12
Legend | [PM] | [FS] | [ENG] | [POST] |  | Assumption-based projects: SimTwin Platform, Mixing Digital Twin, Patents for Software and AIoRT
Projects | [5 empty] | 2025 | [11 empty] | 2026
Project | Tag | Activity | Start | End | Duration | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
SimTwin Platform | [PM] | Project Kickoff | 2025-01-01 | 2025-01-01 | 1 | 1
SimTwin Platform | [FS] | State-of-the-Art Review | 2025-01-01 | 2025-01-31 | 31 | 1
SimTwin Platform | [FS] | Benchmark Study | 2025-02-01 | 2025-02-28 | 28 |  | 1
SimTwin Platform | [FS] | Proof-of-Concept | 2025-03-01 | 2025-03-31 | 31 |  |  | 1
SimTwin Platform | [ENG] | Platform Baseline Development | 2025-04-01 | 2025-06-30 | 91 |  |  |  | 1 | 1 | 1
SimTwin Platform | [ENG] | Connector Development | 2025-07-01 | 2025-09-30 | 92 | [6 empty] | 1 | 1 | 1
SimTwin Platform | [ENG] | Workflow Integration | 2025-10-01 | 2025-12-31 | 92 | [9 empty] | 1 | 1 | 1
SimTwin Platform | [FS] | Testing and Validation | 2026-01-01 | 2026-02-28 | 59 | [12 empty] | 1 | 1
SimTwin Platform | [POST] | Internal Handover | 2026-03-01 | 2026-03-31 | 31 | [14 empty] | 1
SimTwin Platform | [ENG] | Template Library Development | 2026-04-01 | 2026-06-30 | 91 | [15 empty] | 1 | 1 | 1
SimTwin Platform | [ENG] | Performance Hardening | 2026-07-01 | 2026-08-31 | 62 | [18 empty] | 1 | 1
SimTwin Platform | [POST] | Multi-Use-Case Rollout | 2026-09-01 | 2026-10-31 | 61 | [20 empty] | 1 | 1
SimTwin Platform | [PM] | Governance Update | 2026-11-01 | 2026-11-30 | 30 | [22 empty] | 1
SimTwin Platform | [PM] | TRL Analysis | 2026-12-01 | 2026-12-31 | 31 | [23 empty] | 1
Note on A4: Monthly Gantt bars are formula-driven. Edit Start/End dates in this sheet or Timeline_Data and open in Excel to recalculate if needed.