## Gantt
Project Portfolio Gantt Chart
Monthly view • 2025-01 to 2026-12
Legend | [PM] | [FS] | [ENG] | [POST] |  | Assumption-based projects: SimTwin Platform, Mixing Digital Twin, Patents for Software and AIoRT
Projects | [5 empty] | 2025 | [11 empty] | 2026
Project | Tag | Activity | Start | End | Duration | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Patents for Software and AIoRT | [PM] | Project Kickoff | 2026-01-01 | 2026-01-01 | 1 | [12 empty] | 1
Patents for Software and AIoRT | [FS] | Invention Benchmark | 2026-01-01 | 2026-01-15 | 15 | [12 empty] | 1
Patents for Software and AIoRT | [FS] | Prior-Art Review | 2026-01-16 | 2026-02-15 | 31 | [12 empty] | 1 | 1
Patents for Software and AIoRT | [FS] | Patentability Screening | 2026-02-16 | 2026-02-28 | 13 | [13 empty] | 1
Patents for Software and AIoRT | [ENG] | Disclosure Drafting | 2026-03-01 | 2026-03-31 | 31 | [14 empty] | 1
Patents for Software and AIoRT | [ENG] | Claim Drafting | 2026-04-01 | 2026-04-30 | 30 | [15 empty] | 1
Patents for Software and AIoRT | [POST] | Filing Preparation | 2026-05-01 | 2026-05-31 | 31 | [16 empty] | 1
Patents for Software and AIoRT | [POST] | Filing Follow-Up | 2026-06-01 | 2026-07-31 | 61 | [17 empty] | 1 | 1
Patents for Software and AIoRT | [FS] | Portfolio Gap Analysis | 2026-08-01 | 2026-08-31 | 31 | [19 empty] | 1
Patents for Software and AIoRT | [PM] | Commercial Mapping | 2026-09-01 | 2026-10-31 | 61 | [20 empty] | 1 | 1
Patents for Software and AIoRT | [PM] | Portfolio Review | 2026-11-01 | 2026-11-30 | 30 | [22 empty] | 1
Patents for Software and AIoRT | [PM] | TRL Analysis | 2026-12-01 | 2026-12-31 | 31 | [23 empty] | 1
Note on A4: Monthly Gantt bars are formula-driven. Edit Start/End dates in this sheet or Timeline_Data and open in Excel to recalculate if needed.