## TIMELINE V5
Category | Item | PIC | Mandays | 2025-12-01 |  |  |  | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01 |  |  |  | 2026-04-13 |  |  |  | 2026-05-01 |  |  |  | 2026-06-01 |  |  |  | 2026-07-01 |  |  |  | 2026-08-01 |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  | 2026-12-01
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Fixing | MPS (Summary, Dashboard, FG DOI, Prod Sched, etc.) | SWE - ALL | 5 | bar: 2025-12-01 W1
Data (SWE DB) | B7 Capacity Item Data Manager | SWE - Ian | 3 | bar: 2025-12-01 W1
Fixing | MPS Production Plan vs. Capacity | SWE - Fei & Ian | 10 | bar: 2025-12-01 W1 to 2025-12-01 W2
Fixing | MPS Production Schedule Data | SWE - Ian | 3 | bar: 2025-12-01 W2
UI & Integration (SWE DB) | B7 Capacity Item Data Manager | SWE - Bella | 2 | bar: 2025-12-01 W2
UI & Integration (SWE DB) | Audit Log | SWE - Ryu | 3 | bar: 2025-12-01 W2
UI & Integration (SWE DB) | Audit Trail | SWE - Ryu | 3 | bar: 2025-12-01 W2
| Fix Backlog MPS | SWE - ALL | 5 | bar: 2025-12-01 W3 to 2025-12-01 W4
| Prepare production website | DT & SWE | 2 | bar: 2025-12-01 W4 to 2026-01-01 W1
Data (Sim - SWE) | Intermediate Data | DT - All | 4 | bar: 2025-12-01 W2 to 2025-12-01 W3
Integration (SWE DB) | Intermediate Dashboard Calculation FE & SWE DB | SWE - Ian | 5 | bar: 2025-12-01 W3 to 2025-12-01 W4
Integration (SWE DB) | Intermediate Production Schedule | SWE - Ryu | 5 | bar: 2025-12-01 W4
Data (Sim - SWE) | MRP Data | DT - All | 5 | bar: 2025-12-01 W4 to 2026-01-01 W1
Integration (SWE DB) | MRP Dashboard Calculation FE & SWE DB | SWE - Ian | 5 | bar: 2026-01-01 W2 to 2026-01-01 W3
Integration (SWE DB) | MRP Order Summary | SWE - Bella | 5 | bar: 2026-01-01 W2 to 2026-01-01 W4
Integration (SWE DB) | MRP Ending Stock Projection | SWE - Ryu | 5 | bar: 2026-01-01 W2 to 2026-01-01 W3
Recommendation | MRP Recommendation | DT & SWE - Ian & Christopher | 5 | bar: 2026-01-01 W3 to 2026-02-01 W1
Integration (SWE DB) | MRP RMPM Forecast | SWE - Bella | 5 | bar: 2026-01-01 W3 to 2026-01-01 W4
General Functionality | BY Data Ingestion Status State | DT - All | 10 | bar: 2026-01-01 W2 to 2026-01-01 W3
General Functionality | Realtime Update across all modules | SWE - ALL | 10 | bar: 2026-01-01 W3 to 2026-01-01 W4
General Functionality | Backup & Restore | DT & SWE | 20 | bar: 2026-01-01 W3 to 2026-02-01 W2
General Functionality | Remove CRUD Buttons once current module has been locked | SWE - ALL | 5 | bar: 2026-01-01 W3
Authentication | LDAP - CIT | SWE - Ian | 3 | bar: 2026-02-01 W1
Others | Responsive Benchmark | PM & SWE ALL | 10 | bar: 2026-02-01 W1 to 2026-02-01 W2
Others | Deployment to OCP | SWE - Ian | 3 | bar: 2026-02-01 W2
Others | Migrasi Data simulation to oracle | DT | 5 | bar: 2026-02-01 W2
Form UAT | UAT Document | PM | 40 | bar: 2025-12-01 W1 to 2026-02-01 W4
Drafting URS V2 | URS V2 Document | PM | 30 | bar: 2026-02-01 W4 to 2026-03-01 W4
MPS | Improvement Production Capability | SWE | 5 | bar: 2026-03-01 W3
MPS | Improvement Production Capabilit Function | DT | 5 | bar: 2026-03-01 W2
MPS | Improvement item loc DC | SWE | 5 | bar: 2026-03-01 W4
Intermediate | Improvement Dashboard intermediate Tambah Kurang Planorder and depmd | SWE | 5 | bar: 2026-03-01 W4
Intermediate | Improvement Tambah kurang function | DT | 15 | bar: 2026-03-01 W2 to 2026-03-01 W4
MRP | FIX bug Order Summary mrp | DT | 1 | bar: 2026-03-01 W4
MPS | FIX kesanggupan Function | DT | 2 | bar: 2026-03-01 W4
Intermediate | Integrasi Function Tambah Kurang | DT & SWE | 3 | bar: 2026-04-13 W1 to 2026-04-13 W2
MRP & Intermediate | Improvement LOC Inventory dan VLL ending_inventory | DT & SWE | 2 | bar: 2026-04-13 W1 to 2026-04-13 W2
Production | Prepare production website (LDAP + ASSIGN ROLE) | SWE | 3 | bar: 2026-04-13 W3
Production | Sistem Rekomendasi | DT | 2 | bar: 2026-04-13 W2
MPS-MRP | Validasi User | User | 3 | bar: 2026-04-13 W3
UAT | UAT | PM | 5 | bar: 2026-04-13 W4
| Go Live |  | 7 | bar: 2026-04-13 W4 to 2026-05-01 W1
| Realease Note | PM | 5 | bar: 2026-05-01 W1
| Bug fix SLA | CDT | 100 | bar: 2026-05-01 W2 to 2026-09-01 W4
| Database maintenance | CDT | 120 | bar: 2026-05-01 W2 to 2026-11-01 W3
| Application performance monitoring | CDT | 120 | bar: 2026-05-01 W3 to 2026-11-01 W3
| User activity monitoring | CDT | 120 | bar: 2026-05-01 W3 to 2026-11-01 W3
| Evaluasi | CDT | 30 | bar: 2026-05-01 W3 to 2026-12-01 W4
TOTAL MANDAYS |  |  | 774
Total Task | 48
YTD CLA | 90.7%
YTD | 85.42%