## Gantt
Project Portfolio Gantt Chart
Monthly view • 2025-01 to 2026-12
Legend | [PM] | [FS] | [ENG] | [POST] |  | Assumption-based projects: SimTwin Platform, Mixing Digital Twin, Patents for Software and AIoRT
Projects | [5 empty] | 2025 | [11 empty] | 2026
Project | Tag | Activity | Start | End | Duration | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Mixing Digital Twin | [PM] | Project Kickoff | 2025-07-01 | 2025-07-01 | 1 | [6 empty] | 1
Mixing Digital Twin | [FS] | State-of-the-Art Review | 2025-07-01 | 2025-07-31 | 31 | [6 empty] | 1
Mixing Digital Twin | [FS] | Benchmark Study | 2025-08-01 | 2025-08-31 | 31 | [7 empty] | 1
Mixing Digital Twin | [FS] | Proof-of-Concept | 2025-09-01 | 2025-09-30 | 30 | [8 empty] | 1
Mixing Digital Twin | [ENG] | Baseline Modeling | 2025-10-01 | 2025-11-30 | 61 | [9 empty] | 1 | 1
Mixing Digital Twin | [ENG] | Parameter Calibration | 2025-12-01 | 2026-01-31 | 62 | [11 empty] | 1 | 1
Mixing Digital Twin | [FS] | Testing and Validation | 2026-02-01 | 2026-03-31 | 59 | [13 empty] | 1 | 1
Mixing Digital Twin | [POST] | Acceptance Review | 2026-04-01 | 2026-04-30 | 30 | [15 empty] | 1
Mixing Digital Twin | [ENG] | Scenario Library Development | 2026-05-01 | 2026-06-30 | 61 | [16 empty] | 1 | 1
Mixing Digital Twin | [ENG] | Optimization Study | 2026-07-01 | 2026-08-31 | 62 | [18 empty] | 1 | 1
Mixing Digital Twin | [POST] | Engineering Workflow Integration | 2026-09-01 | 2026-10-31 | 61 | [20 empty] | 1 | 1
Mixing Digital Twin | [PM] | Playbook Drafting | 2026-11-01 | 2026-11-30 | 30 | [22 empty] | 1
Mixing Digital Twin | [PM] | TRL Analysis | 2026-12-01 | 2026-12-31 | 31 | [23 empty] | 1
Note on A4: Monthly Gantt bars are formula-driven. Edit Start/End dates in this sheet or Timeline_Data and open in Excel to recalculate if needed.