## 2025 V2 (Best Case)
Task Subject | Plan Start | Plan End | Actual Start | Actual End
[PM] - URS Creation | 2025-10-01 | 2025-11-21 | 2025-10-01 | 2025-11-21
[PM] - URS Approval | 2025-11-15 | 2025-12-07 | 2025-11-15 | 2025-12-07
[UI] - Create UI | 2025-10-01 | 2025-10-31 | 2025-10-01 | 2025-10-31
[UI] - Login Page | 2025-10-01 | 2025-10-07 | 2025-10-01 | 2025-10-07
[UI] - Chatbot UI | 2025-10-01 | 2025-10-07 | 2025-10-01 | 2025-10-07
[AI] - Discovery & Architecture | 2025-10-01 | 2025-10-21 | 2025-10-01 | 2025-10-21
[AI] - Environment & Vector Store Setup | 2025-10-08 | 2025-10-28 | 2025-10-08 | 2025-10-28
[AI] - Ingestion Pipeline - Include Layout Detection - Include OCR - Include img2table - Multi-column handling | 2025-10-15 | 2025-11-28 | 2025-10-15 | 2025-11-28
[AI] - Retrieval and Prompting | 2025-10-22 | 2025-11-28 | 2025-10-22 | 2025-11-28
[AI] - Experimenting with Different LLM | 2025-10-22 | 2025-10-31 | 2025-10-22 | 2025-10-31
[AI] - Validation & Guardrails | 2025-11-08 | 2025-12-14 | 2025-11-08 | 2025-12-14
[AI] - Lobechat Integration | 2025-11-15 | 2025-11-28 | 2025-11-15 | 2025-11-28
[AI] - Reranking & Tuning | 2025-11-22 | 2025-12-07 | 2025-11-22 | 2025-12-07
[AI] - Security, Roles, & Observability | 2025-12-08 | 2025-12-21 | 2025-12-08 | 2025-12-21
[AI] - AI Deployment | 2025-12-15 | 2025-12-31 | 2025-12-15 | 2025-12-31
[SWE] - Connect FE to Biomni | 2025-10-08 | 2025-11-07 | 2025-10-08 | 2025-11-07
[SWE] - Paper Management UI | 2025-10-08 | 2025-10-14 | 2025-10-08 | 2025-10-14
[SWE] - Paper Management BE | 2025-10-15 | 2025-10-31 | 2025-10-15 | 2025-10-31
[SWE] - User Management -RBAC | 2025-10-29 | 2025-10-31 | 2025-10-29 | 2025-10-31
[SWE] - Audit Trail -UI | 2025-11-01 | 2025-11-07 | 2025-11-01 | 2025-11-07
[SWE] - Audit Trail BE | 2025-11-08 | 2025-11-28 | 2025-11-08 | 2025-11-28
[SWE] - Bug Fixing and Improvement | 2025-12-01 | 2025-12-21 | 2025-12-01 | 2025-12-21
[SWE] - Deployment to Staging Cloud | 2025-12-08 | 2025-12-21 | 2025-12-08 | 2025-12-21
[BioLLM & BioPaperExtractor] Design/propose validation method for retrieval system | 2026-01-15 | 2026-01-21 | 2026-01-15 | 2026-01-21
[BioLLM] Design/propose validation method for end-to-end LLM chatbot | 2026-01-15 | 2026-02-07 | 2026-01-15 | 2026-02-07
[BioPaperExtractor] Create Evaluation Pipeline using the agreed 2-stage evaluation metrics | 2026-01-15 | 2026-02-14 | 2026-01-15 | 2026-02-14
[KalbeGPT] User Management -RBAC | 2026-02-01 | 2026-02-14 | 2026-02-01 | 2026-02-14
[BioLLM] Validator Feedback Execution | 2026-01-01 | 2026-01-14 | 2026-01-01 | 2026-01-14
[BioLLM] Evaluate feasibility and performance of AWS embedding vs Open AI embedding model | 2026-01-15 | 2026-01-28 | 2026-01-15 | 2026-01-28
[BioLLM] Improve agent capability based on Validator feedback | 2026-01-22 | 2026-03-07 | 2026-01-22 | 2026-03-07
[BioPaperExtractor] Run evaluation on current Paper Extractor implemented algorithm | 2026-02-08 | 2026-03-21 | 2026-02-08 | 2026-03-21
[BioLLM] Migrate from cloud infra to on prem (Staging) | 2026-02-08 | 2026-03-14 | 2026-02-08 | 2026-03-14
[BioLLM] UAT | 2026-03-15 | 2026-03-21 | 2026-03-15 | 2026-03-21
[BioLLM] Deliver BioLLM | 2026-03-15 | 2026-03-21 | 2026-03-15 | 2026-03-21
[BioLLM & BioPaperExtractor] Improvement the AI Assistant | 2026-04-01 | 2026-07-21 | 2026-04-01
[BioLLM] Create 2nd Data Ingestion pipeline (+ caching) to accommodate AWS stack | 2026-04-01 | 2026-05-28 | 2026-04-01
[BioLLM] Ingest Paper using AWS Embedding | 2026-04-01 | 2026-05-28 | 2026-04-01
[BioPaperExtractor] UAT & Human Feedback BioPaperExtractor | 2026-04-22 | 2026-04-28
[BioPaperExtractor] Deliver BioPaperExtractor | 2026-04-22 | 2026-04-28
[BioLLM & BioPaperExtractor] UAT & Human Feedback (after migrate to AWS) | 2026-06-01 | 2026-06-07
[KalbeGPT] Deployment on prem and Server Ready | 2026-06-01 | 2026-06-21