## Task Tracker
Enterprise RAG Trust Layer v2 — Task Tracker (Kalbe Environment)
Project: Enterprise RAG ¦ Active Phase: 3 — Touch Up ¦ Tracking: Monthly (MTD & YTD)
Legend: ✅ Done 🔄 In Progress ⬜ Planned (Plan Start / Plan End / Actual Start / Actual End — fill manually)
Task ID | Task Subject | Status | Plan Start | Plan End | Actual Start | Actual End
PHASE 1 — FEASIBILITY STUDY
1.1 Technical & Infrastructure Study
1.1.1.1 | Evaluasi kebutuhan retrieval & search | ✅ Done
1.1.1.2 | Evaluasi vector database options | ✅ Done
1.1.1.3 | Evaluasi LLM provider (Claude, GPT, Gemini) | ✅ Done
1.2 Business Analysis
1.2.1.1 | Identifikasi use case bisnis Kalbe | ✅ Done
1.2.1.2 | Mapping data sources Kalbe (PDF, DB, Web) | ✅ Done
1.3 Architecture & Documentation
1.3.1.1 | Pemilihan tech stack final | ✅ Done
1.4.1.1 | Penulisan feasibility report | ✅ Done
PHASE 2 — BUILD PLATFORM
2.1 RAG Online Query & Retrieval Pipeline
2.1.1.1 | Setup Application UI (chat/search/API interface) | ✅ Done
2.1.2.1 | Setup API Gateway & routing (FastAPI/Kong) | ⬜ Planned
2.1.3.1 | Setup Conversation Store — Redis/PostgreSQL | ✅ Done
2.1.4.1 | Implementasi Sparse Search BM25 (Elasticsearch) | ✅ Done
2.1.5.1 | Implementasi Dense Search Semantic (Qdrant/Weaviate) | ✅ Done
2.1.6.1 | Implementasi Hybrid Merge & Fusion RRF | ✅ Done
2.1.7.1 | Implementasi Cross-encoder Reranker (Cohere/FlashRank) | ✅ Done
2.1.8.1 | Integrasi Domain APIs (PubMed, SEC) | ✅ Done
2.1.9.1 | Integrasi Web Search (Tavily/SerpAPI/Bing) | ⬜ Planned
2.1.10.1 | Implementasi External Merge & Filter | ⬜ Planned
2.1.11.1 | Implementasi Circuit Breakers (fallback/graceful degrade) | ⬜ Planned
2.2 Document Ingestion & Indexing Pipeline
2.2.1.1 | Setup Raw Data Sources ingestion (PDF, DOCX, Web, DB) | ✅ Done
2.2.2.1 | Setup Doc Loader & Storage (S3/Supabase) | ✅ Done
2.2.3.1 | Implementasi Extraction pipeline (Tika/PDFMiner) | ✅ Done
2.2.4.1 | Implementasi Dedup & Version control (MinHash/SimHash) | ✅ Done
2.2.5.1 | Implementasi Chunking & Embedding | ✅ Done
2.2.6.1 | Setup Vector Database (Qdrant/Weaviate) | ✅ Done
2.2.7.1 | Setup Metadata Store (PostgreSQL/Qdrant) | ✅ Done
2.3 Context Processing & Protection
2.3.1.1 | Implementasi Secure Data Retrieval — OPA/Casbin ACL | ✅ Done
2.3.2.1 | Implementasi Dynamic Grounding (LangChain Callbacks) | ✅ Done
2.3.3.1 | Implementasi Data Masking PII/PHI (MS Presidio/Google DLP) | ⬜ Planned
2.4 Secure Gateway & Zero Data Retention
2.4.1.1 | Setup Secure Gateway TLS & rate limiting (Portkey/Kong) | ⬜ Planned
2.4.2.1 | Implementasi Zero Data Retention enforcement (AWS Bedrock BAA) | ⬜ Planned
2.4.3.1 | Config drift detection & SLA validation (Azure OpenAI DPA) | ⬜ Planned
2.5 Generation Pipeline
2.5.1.1 | Implementasi Prompt Assembly (system instruction, grounding) | ✅ Done
2.5.2.1 | Integrasi Large Language Model (Claude Sonnet / GPT-4o) | ✅ Done
2.6 Post-Generation Pipeline
2.6.1.1 | Implementasi Evidence-Based Verifier (grounding score/Ragas) | ✅ Done
2.6.2.1 | Implementasi Toxicity & Safety Filter (OpenAI Moderation) | ⬜ Planned
2.6.3.1 | Implementasi Domain Rule Engine (business logic/OPA) | ⬜ Planned
2.6.4.1 | Implementasi Data Demasking (Presidio reverse) | ⬜ Planned
2.6.5.1 | Setup Inline Audit Trail fail-closed logging (LangFuse/LangSmith) | 🔄 In Progress
2.7 Deployment Setup
2.7.1.1 | Setup On-Prem / Private Cloud deployment (Keycloak/OPA/Drools) | 🔄 In Progress
2.7.2.1 | Setup Managed Cloud w/ BAA/DPA (AWS Bedrock/Azure) | ⬜ Planned
2.7.3.1 | Setup Self-Hosted LLM max privacy (Llama3/Mistral/Ollama) | ⬜ Planned
PHASE 3 — TOUCH UP (KALBE ENVIRONMENT) ← ACTIVE
3.1 Environment Configuration
3.1.1.1 | Inventarisasi env variables yang perlu diganti | 🔄 In Progress
3.1.1.2 | Setup .env file Kalbe (non-prod) | 🔄 In Progress
3.1.1.3 | Setup .env file Kalbe (prod) | ⬜ Planned
3.1.1.4 | Validasi koneksi ke internal network Kalbe | ⬜ Planned
3.1.2.1 | Mapping data source Kalbe — identifikasi format | 🔄 In Progress
3.1.2.2 | Konfigurasi connector ke database Kalbe | 🔄 In Progress
3.1.2.3 | Test ingestion dokumen sample Kalbe | ⬜ Planned
3.1.3.1 | Konfigurasi Keycloak realm Kalbe | 🔄 In Progress
3.1.3.2 | Integrasi SSO Kalbe ke Application UI | ⬜ Planned
3.1.3.3 | Test login flow end-to-end | ⬜ Planned
3.1.4.1 | Mapping compliance rules Kalbe ke OPA policies | ⬜ Planned
3.1.4.2 | Uji coba OPA policy enforcement | ⬜ Planned
3.2 Integration Testing
3.2.1.1 | Buat test case retrieval pipeline | ⬜ Planned
3.2.1.2 | Eksekusi test retrieval (sparse, dense, hybrid) | ⬜ Planned
3.2.1.3 | Dokumentasi hasil & bug report retrieval | ⬜ Planned
3.2.2.1 | Buat test case ingestion pipeline | ⬜ Planned
3.2.2.2 | Eksekusi test ingestion dokumen Kalbe | ⬜ Planned
3.2.3.1 | Buat test case generation pipeline | ⬜ Planned
3.2.3.2 | Eksekusi test generation (grounding, accuracy) | ⬜ Planned
3.2.3.3 | Dokumentasi hasil & bug report generation | ⬜ Planned
3.3 Security & Compliance
3.3.1.1 | Penetration test planning & scope definition | ⬜ Planned
3.3.1.2 | Eksekusi pentest (API, Auth, Data layer) | ⬜ Planned
3.3.1.3 | Remediasi temuan pentest | ⬜ Planned
3.3.2.1 | Audit data privacy sesuai kebijakan Kalbe | ⬜ Planned
3.3.2.2 | Dokumentasi compliance checklist | ⬜ Planned
3.4 Performance Tuning
3.4.1.1 | Setup load testing tool (Locust/k6) | ⬜ Planned
3.4.1.2 | Eksekusi load test (concurrent users simulation) | ⬜ Planned
3.4.1.3 | Dokumentasi benchmark results | ⬜ Planned
3.4.2.1 | Identifikasi bottleneck latency | ⬜ Planned
3.4.2.2 | Optimasi query retrieval (caching, indexing) | ⬜ Planned
3.4.2.3 | Optimasi generation response time | ⬜ Planned
3.5 User Acceptance Testing (UAT)
3.5.1.1 | Persiapan UAT plan & skenario pengujian | ⬜ Planned
3.5.1.2 | Onboarding user internal Kalbe untuk UAT | ⬜ Planned
3.5.1.3 | Eksekusi UAT session (supervised) | ⬜ Planned
3.5.1.4 | Kompilasi & analisis feedback UAT | ⬜ Planned
3.5.2.1 | Prioritisasi & fix bug dari hasil UAT | ⬜ Planned
3.5.2.2 | Regression test setelah bug fix | ⬜ Planned
3.5.2.3 | Sign-off UAT dari stakeholder Kalbe | ⬜ Planned
PHASE 4 — RELEASE Q2
4.1 Go-Live Preparation
4.1.1.1 | Go-live checklist & readiness review | ⬜ Planned
4.1.1.2 | Runbook & rollback plan documentation | ⬜ Planned
4.2 Production Deployment
4.2.1.1 | Production deployment execution | ⬜ Planned
4.2.1.2 | Smoke test post-deployment | ⬜ Planned
4.3 Monitoring & Hypercare
4.3.1.1 | Setup monitoring & alerting dashboard post go-live | ⬜ Planned
4.3.1.2 | Hypercare support — 2 minggu pertama | ⬜ Planned
4.4 Release Documentation
4.4.1.1 | Penulisan release notes | ⬜ Planned
4.4.1.2 | Dokumentasi teknis final v1.0 | ⬜ Planned
PHASE 5 — IMPROVEMENT v2.0 (TARGET Q4)
5.1 Gap Analysis & Feature Study
5.1.1.1 | Gap analysis fitur v1 vs kebutuhan Kalbe v2 | 🔄 In Progress
5.1.1.2 | Feature study & benchmarking kompetitor | 🔄 In Progress
5.2 Prompt Defense Enhancement
5.2.1.1 | Implementasi Prompt Defense jailbreak prevention (Rebuff/LLM Guard) | ⬜ Planned
5.2.2.1 | Implementasi Intent Router enhancement (LangGraph/NVidia) | ⬜ Planned
5.3 Data Masking & PII Protection
5.3.1.1 | Implementasi PII/PHI masking lanjutan (MS Presidio/AWS Comprehend) | ⬜ Planned
5.3.2.1 | Implementasi reversible token mapping (Custom Middleware) | ⬜ Planned
5.4 Toxicity & Domain Safety Filter v2
5.4.1.1 | Implementasi Toxicity filter v2 (Perspective API) | ⬜ Planned
5.4.2.1 | Domain safety rule expansion (Slack-bert / Custom) | ⬜ Planned
5.5 Domain Rule Engine v2
5.5.1.1 | Domain Rule Engine v2 schema validation (OPA/Drools) | ⬜ Planned
5.6 Advanced Intent Router
5.6.1.1 | Advanced Intent Classification (LangGraph/Semantic Router) | ⬜ Planned
5.7 Deployment v2.0 & Go-Live
5.7.1.1 | Deployment v2.0 ke staging environment | ⬜ Planned
5.7.2.1 | UAT v2.0 | ⬜ Planned
5.7.3.1 | Go-live v2.0 | ⬜ Planned

## MTD-YTD Summary
MTD & YTD Progress Summary — Enterprise RAG Trust Layer v2
Fill 'Actual End' in Task Tracker sheet → update counts below manually each month
Metric | MTD (This Month) | YTD (This Year) | Notes
Total Tasks | — | 112 tasks total | All phases combined
✅ Tasks Completed |  |  | Count tasks with Actual End filled
🔄 Tasks In Progress
⬜ Tasks Planned
Overall Progress (%) |  |  | Update manually
Phase 1 — Feasibility | 7/7 | 100% | ✅ Complete
Phase 2 — Build Platform
Phase 3 — Touch Up (Active) |  |  | 🔄 In Progress
Phase 4 — Release Q2 |  |  | ⬜ Not started
Phase 5 — v2.0 (Q4) |  |  | 🔄 Partially started
Blockers / Risks
Target Next Month